## SYSTEM PRODUCT BACKLOG
PROJECT PRODUCT BACKLOG |  |  | Assignment |  | STATUS KEY
UR# | Priority | Status | Team Member | Sprint | OPEN
1 | Welcome sequence: A user can set up a welcome sequence that automatically sends a series of welcome emails to new subscribers, introducing them to the brand and its products or services. | OPEN | George |  | CLOSED
2 | Drip campaigns: A user can create drip campaigns that send a series of targeted emails to prospects or customers over a specified period, based on triggers like sign-ups, clicks, or opens. | OPEN | George
3 | Abandoned cart recovery: A user can set up an automated email sequence that sends a reminder to customers who have abandoned their shopping carts, encouraging them to complete their purchase. | OPEN | George
4 | Event invitations: A user can send personalized invitations and reminders to attendees of upcoming events, including registration links, agendas, and logistical details. | OPEN | George
5 | Newsletters: A user can create and send regular newsletters to subscribers, containing news, updates, promotions, or curated content, with the option to segment the audience by interests or behavior. | OPEN | George
6 | Post-purchase follow-ups: A user can send automated emails to customers after they have made a purchase, thanking them for their business, requesting feedback or reviews, or suggesting complementary products or services. | OPEN | George
7 | Lead nurturing: A user can create an email sequence that nurtures leads over time, educating them about the brand, its values, and its solutions, with the goal of converting them into customers. | OPEN | George
8 | Anniversary or birthday campaigns: A user can set up automated campaigns that send personalized messages to customers on their birthdays or anniversaries, offering special promotions, discounts, or gifts. | OPEN | George
9 | Reactivation campaigns: A user can send automated messages to subscribers who haven't opened or clicked on emails for a while, trying to re-engage them with the brand and its offerings. | OPEN | George
10 | Feedback requests: A user can send automated surveys or feedback requests to customers or subscribers, asking for their opinions, suggestions, or complaints, and using the insights to improve the products or services. | OPEN | George
11 |  | OPEN
12 |  | OPEN
13 |  | OPEN
14 |  | OPEN
15 |  | OPEN
16 |  | OPEN
17 |  | OPEN
18 |  | OPEN
19 |  | OPEN
20 |  | OPEN
21 |  | OPEN
22 |  | OPEN
23 |  | OPEN
24 |  | OPEN
25 |  | OPEN
26 |  | OPEN
27 |  | OPEN
28 |  | OPEN
29 |  | OPEN
30 |  | OPEN
31 |  | OPEN
32 |  | OPEN
33 |  | OPEN
34 |  | OPEN
35 |  | OPEN
36 |  | OPEN
37 |  | OPEN
38 |  | OPEN
39 |  | OPEN
40 |  | OPEN
41 |  | OPEN
42 |  | OPEN
43 |  | OPEN
44 |  | OPEN
45 |  | OPEN
46 |  | OPEN
47 |  | OPEN
48 |  | OPEN
49 |  | OPEN
50 |  | OPEN

## SPRINT 1 BACKLOG
SPRINT 1 BACKLOG |  |  |  | Assignment | STATUS KEY
UR# | Item | Priority | Status | Team Member | OPEN
1 | Title Page | low | Closed | Tamara Villaroel | CLOSED
2 | Table of Contents | low | Closed | Tamara Villaroel
3 | Section 1 Executive Summary with Narrative and Conclusions | low | Closed | Brian Fantaci
4 | Company Background & Current Environment | low | Closed | Brian Fantaci
5 | Problem Analysis (BPA, BPI, BPR) | Low | Closed | George Booth
6 | Proposed System Objectives and Constraints | Low | Closed | George Booth
7 | Expected Benefits | Low | Closed | Izzy Andresen
8 | Context Diagram | Low | Closed | Tamara Villaroel
9 | Use Case Diagram | Low | Closed | Tamara Villaroel
10 | Executive Summary with Narrative and Conclusions for Section 2 Analysis | Low | Closed | Brian Fantaci
11 | Preliminary Supplement Specifications (Non-functional Requirements) | Low | Closed | Izzy Andresen
12 | Updated Context Diagram | Low | Closed | Tamara Villaroel
13 | Updated Use Case Diagram | Low | Closed | Tamara Villaroel
14 | Updated Product Backlog | Low | Closed | Tamara Villaroel
15 | Sprint 2 Backlog | Low | Closed | Brian Fantaci
16 | Sprint 2 Burn Down Chart | Low | Closed | George Booth
17 | Sprint 2 PSPI | Low | Closed | Tamara Villaroel
18 | Introduction to the SR&R 2 Presentation | Low | Closed | Izzy Andresen
19 | Section 3 Executive Summary with Narrative and Conclusion | Low | Closed | Izzy Andresen
20 | Complete Data Flow Diagram Package ▪ DFD Level 0 ▪ One or two DFD Level 1 | Low | Closed | Tamara Villaroel
21 | Hardware and Software Specifications | Low | Closed | George Booth
22 | Navigation Diagram | Low | Closed | George Booth
23 | Physical Entity-Relationship Diagram (ERD | Low | Closed | George Booth
24 | Program Plan – IPO Chart | Low | Closed | Brian Fantaci
25 | Updated Context Diagram | Low | Closed | Tamara Villaroel
26 | Detailed Supplement Specifications (Non-functional Requirements) | Low | Closed | George Booth
27 | Updated Product Backlog | Low | Closed | Brian Fantaci
28 | Sprint 3 Backlog | Low | Closed | Brian Fantaci
29 | Sprint 3 Burndown Chart | Low | Closed | George Booth

## SPRINT 2 BACKLOG
SPRINT 2 BACKLOG |  |  |  | Assignment | STATUS KEY
UR# | Item | Priority | Status | Team Member | OPEN
10 | Executive Summary with Narrative and Conclusions for Section 2 Analysis | Low | Closed | Brian Fantaci | CLOSED
11 | Preliminary Supplement Specifications (Non-functional Requirements) | Low | Closed | Izzy Andresen
12 | Updated Context Diagram | Low | Closed | Tamara Villaroel
13 | Updated Use Case Diagram | Low | Closed | Tamara Villaroel
14 | Updated Product Backlog | Low | Closed | Tamara Villaroel
15 | Sprint 2 Backlog | Low | Closed | Brian Fantaci
16 | Sprint 2 Burn Down Chart | Low | Closed | George Booth
17 | Sprint 2 PSPI | Low | Closed | Tamara Villaroel
18 | Introduction to the SR&R 2 Presentation | Low | Closed | Izzy Andresen

## SPRINT 3 BACKLOG
SPRINT 3 BACKLOG |  |  |  | Assignment | STATUS KEY
UR# | Item | Priority | Status | Team Member | OPEN
19 | Section 3 Executive Summary with Narrative and Conclusion | Low | Closed | Izzy Andresen | CLOSED
20 | Complete Data Flow Diagram Package ▪ DFD Level 0 ▪ One or two DFD Level 1 | Low | Closed | Tamara Villaroel
21 | Hardware and Software Specifications | Low | Closed | George Booth
22 | Navigation Diagram | Low | Closed | George Booth
23 | Physical Entity-Relationship Diagram (ERD | Low | Closed | George Booth
24 | Program Plan – IPO Chart | Low | Closed | Brian Fantaci
25 | Updated Context Diagram | Low | Closed | Tamara Villaroel
26 | Detailed Supplement Specifications (Non-functional Requirements) | Low | Closed | George Booth
27 | Updated Product Backlog | Low | Closed | Brian Fantaci
28 | Sprint 3 Backlog | Low | Closed | Brian Fantaci
29 | Sprint 3 Burndown Chart | Low | Closed | George Booth

## SPRINT 4 BACKLOG
SPRINT 4 BACKLOG |  |  |  | Assignment | STATUS KEY
UR# | Item | Priority | Status | Team Member | OPEN
CLOSED

## SPRINT 5 BACKLOG
SPRINT 5 BACKLOG |  |  |  | Assignment | STATUS KEY
UR# | Item | Priority | Status | Team Member | OPEN
CLOSED

## SPRINT 6 BACKLOG
SPRINT 6 BACKLOG |  |  |  | Assignment | STATUS KEY
UR# | Item | Priority | Status | Team Member | OPEN
CLOSED