## Sprint 1 Burndown
Backlog Item ID | User Stories / Requirements / Bugs | Estimated Time | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Team Member | Total Time
| Title Page | 0.5 | Day 1: 0.25 | George Booth | 8
| Table of Contents | 0.5 | Day 3: 0.25; Day 10: 0.25 | Tamara Villarroe | 9
| Section 1 Executive Summary with Narrative and Conclusions | 0.5 | Day 5: 0.25; Day 12: 0.25 | Izzy Andresen | 7
| Company Background & Current Environment | 2 | Day 3: 0.25; Day 7: 0.25; Day 11: 0.5; Day 13: 1 | Brian Fantaci​ | 8
| Problem Analysis (BPA, BPI, BPR) | 2 | Day 4: 0.5; Day 7: 0.5; Day 11: 0.5; Day 13: 1 |  | 32 | Total Team Time
| Proposed System Objectives and Constraints | 2 | Day 5: 1; Day 9: 0.25; Day 12: 1
| Expected Benefits | 2 | Day 5: 0.5; Day 9: 1
| Context Diagram | 1 | Day 6: 0.5; Day 10: 0.25; Day 13: 0.5
| Group Meetings | 5 | Day 1: 1; Day 4: 1; Day 7: 2; Day 12: 1; Day 14: 0.5
| Talking to Client | 1 | Day 3: 0.25; Day 8: 0.75
Remaining Effort |  | 16.5 | 15.25 | 15.25 | 14.5 | 13 | 11.25 | 10.75 | 8 | 7.25 | 6 | 5.5 | 4.5 | 2.25 | -0.25 | -0.75
Ideal Effort |  | 16.5 | 15.3214 | 14.1429 | 12.9643 | 11.7857 | 10.6071 | 9.4286 | 8.25 | 7.0714 | 5.8929 | 4.7143 | 3.5357 | 2.3571 | 1.1786 | -3.1086e-15

## Sprint 2 Burndown
Backlog Item ID | User Stories / Requirements / Bugs | Estimated Time | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Team Member | Total Time
| Section 2 Executive Summary with Narrative and Conclusions | 1 | Day 2: 0.25; Day 4: 0.25; Day 8: 0.5; Day 12: 0.25 | George Booth | 8
| Use Case Diagram | 2 | Day 1: 0.25; Day 5: 1; Day 9: 0.5; Day 14: 0.25 | Tamara Villarroe | 8
| Supplement Specifications (Non-Functional) | 2 | Day 3: 0.25; Day 7: 0.25; Day 11: 1.25; Day 13: 0.25 | Izzy Andresen | 6
| Group meetings | 1 | Day 1: 0.25; Day 4: 0.25; Day 6: 0.25; Day 12: 0.25 | Brian Fantaci​ | 7
[18 empty] | 29 | Total Team Time
Remaining Effort |  | 6 | 5.5 | 5.25 | 5 | 4.5 | 3.5 | 3.25 | 3 | 2.5 | 2 | 2 | 0.75 | 0.25 | 0 | -0.25
Ideal Effort |  | 6 | 5.5714 | 5.1429 | 4.7143 | 4.2857 | 3.8571 | 3.4286 | 3 | 2.5714 | 2.1429 | 1.7143 | 1.2857 | 0.85714 | 0.42857 | 0

## Sprint 3 Burndown
Backlog Item ID | User Stories / Requirements / Bugs | Estimated Time | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21 | Team Member | Total Time
| Section 3 Executive Summary with Narrative and Conclusions | 0.75 | Day 2: 0.25; Day 7: 0.25; Day 16: 0.25 | George Booth | 9
| Complete Data Flow Diagram Package | 1 | Day 3: 0.25; Day 9: 1; Day 14: 1; Day 20: 0.75 | Tamara Villarroe | 8
| Hardware and Software Specification | 1.5 | Day 2: 1; Day 13: 0.25; Day 18: 1 | Izzy Andresen | 7
| Navigation Diagram | 1 | Day 1: 0.25; Day 5: 0.25; Day 17: 0.25 | Brian Fantaci​ | 8
| Entity Relationship Diagrams | 2 | Day 3: 1; Day 9: 1; Day 14: 0.25; Day 19: 0.75 |  | 32 | Total Team Time
| Program Plan showing logic and I/Os (IPO Chart with each program listed) | 1 | Day 2: 0.25; Day 10: 0.75; Day 17: 0.25
Remaining Effort |  | 7.25 | 7 | 5.5 | 4.25 | 4.25 | 4 | 4 | 3.75 | 3.75 | 1.75 | 1 | 1 | 1 | 0.75 | -0.5 | -0.5 | -0.75 | -1.25 | -2.25 | -3 | -3.75 | -3.75
Ideal Effort |  | 7.25 | 6.7321 | 6.2143 | 5.6964 | 5.1786 | 4.6607 | 4.1429 | 3.625 | 3.1071 | 2.5893 | 2.0714 | 1.5536 | 1.0357 | 0.51786 | -1.9984e-15 | -0.51786 | -1.0357 | -1.5536 | -2.0714 | -2.5893 | -3.1071 | -3.625

## Sprint 4 Burndown
Backlog Item ID | User Stories / Requirements / Bugs | Estimated Time | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21 | Team Member | Total Time
George Booth
Tamara Villarroe
Izzy Andresen
Brian Fantaci​
[25 empty] | 0 | Total Team Time
Remaining Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ideal Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint 5 Burndown
Backlog Item ID | User Stories / Requirements / Bugs | Estimated Time | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Team Member | Total Time
George Booth
Tamara Villarroe
Izzy Andresen
Brian Fantaci​
[18 empty] | 0 | Total Team Time
Remaining Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ideal Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint 6 Burndown
Backlog Item ID | User Stories / Requirements / Bugs | Estimated Time | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Team Member | Total Time
George Booth
Tamara Villarroe
Izzy Andresen
Brian Fantaci​
[18 empty] | 0 | Total Team Time
Total Project Time
[18 empty] | Sprint 1 | 32
[18 empty] | Sprint 2 | 29
[18 empty] | Sprint 3 | 32
[18 empty] | Sprint 4 | 0
[18 empty] | Sprint 5 | 0
[18 empty] | Sprint 6 | 0
[19 empty] | 93 | Total Project Time
Remaining Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ideal Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0